## Sheet1
Project Name |  | Blog Testing | Environment | Staging
Tester's Name |  | Rahat Ahmed Shafi | Reviewed By | Team Lead
Date Tested |  | 2025-11-05 | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment
1 | Articles | Page not found | When click to read more option that does not show the page | 1. The user goes to Article page. 2. Click the read more option | Bug | Medium | Moderate | No page shown | Page must be shown | https://academybugs.com/why-do-i-need-financial-consulting-services
2 | social share buttons | The social share buttons don't lead to anywhere | When user try to share something then the social button does not work | 1. User goes to social field. 2. post something | Bug | High | Major | The social share buttons don't lead to anywhere | To be able to share posts using the social media share buttons | https://academybugs.com/articles/
3 | contact-us-form | an error message is displayed | After filling out the form and clicking the "Send" button, an error message is displayed | 1. User goes to contact-us-form. 2. Insert valid name 3. Insert valid email 4. Insert Subject 5. Insert message 6. Tap Send Button | Bug | High | Moderate | After filling out the form and clicking the "Send" button, an error message is displayed | The message is sent through the contact us form | https://academybugs.com/contact-us-form/
4 | Video player | Video player doesn’t work | Video players should quickly buffer and play video files, but in this example some videos can’t be played. | 1. User goes to latest-news page. 2. Click paly button | Improvement | Low | Minor | A black screen is shown instead of videos in the left column | The videos in the left column are played back | https://academybugs.com/latest-news/
5 | Reservation | the user cannot submit the booking form. | The user should be able to book a table, but in this example the user cannot submit the booking form. | 1. User goes to Booking page. 2. Insert valid Date 3. Insert valid Time 4. Insert Party 5. Insert Name 6. Insert valid email 7.Insert Valid Phone Number 8. Tap Request Booking Button | Bug | High | Moderate | The same page is shown again | The form is submitted successfully and a confirmation message is shown | https://academybugs.com/my-bookings/